## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group N | Completed | 11
Project title | Big Brother Student Accommodation Management System | In Progress | 0
Stakeholder or organisation | Big Brother Student Accommodation | Not Started | 0
Group mentor | N Mabanza, M Mbele, N Grobbelaar | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 18 August 2026 - 31 August 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 91.67% | Contribution Summary | Count
Main achievement | Stakeholder interview completed and initial stakeholder needs and problems identified. | Contribution entries | 10
Main challenge | Managing project scope and completing all required functionality within the period | Verified entries | 10
Next planned activity | Complete Unit 1 Activities 1.1–1.3 documentation and update the project tracker | Unverified entries | 0
|  | Stakeholder engagements | 1

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | NL Mazibuko | 2026-08-19 | 2026-08-31 | Completed | 100 | Stakeholder and Problem Analysis.docx | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | PA Mabusela | 2026-08-26 | 2026-08-31 | Completed | 100 | Software Requirement Specification.docx | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | MN Dlamini, NP Khotle | 2026-08-24 | 2026-08-31 | Completed | 100 | Non-Functional, System & Integration Requirements.pdf | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | NP Khotle, MN Dlamini | 2026-08-24 | 2026-08-31 | Completed | 100 | Stakeholder and Problem Analysis.docx | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | AL Hadebe, PA Mabusela, NL Mazibuko | 2026-08-25 | 2026-08-31 | Completed | 100 | Stakeholder and Problem Analysis.docx | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | MN Dlamini | 2026-08-25 | 2026-08-31 | Completed | 100 | ITC327W_Work Integrated Learning(1).pdf | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | LW Simelane | 2026-08-19 | 2026-08-31 | Completed | 100 | WIL Project.mpp | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | NL Mazibuko | 2026-08-26 | 2026-08-31 | Completed | 100 | Github link: https://github.com/NhlanhlayethuMazibuko/ITC327W-Group-Project.git | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | AL Hadebe | 2026-08-26 | 2026-08-31 | Completed | 100 | Supabase link: https://supabase.com/dashboard/project/gtpujwmtglyffnzhbklo | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | JO Molaba | 2026-08-24 | 2026-08-31 | Completed | 100 | ITC327W Project Progress Tracker.xlsx | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | JO Molaba, with group input | 2026-08-25 | 2026-08-31 | Completed | 100 | ITC327W Project Progress Tracker.xlsx | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
NL Mazibuko | 222044762 | Unit 1 / Phase 1 | Activity 1.1 and Activity 1.3 | Stakeholder Liaison & Problem Analysis Lead/ Github set up | Identified and confirmed the external stakeholder, documented the stakeholder profile, investigated the current accommodation process, contributed to the problem statement, and created the project GitHub repository. | 2026-08-25 | 5 hours | 1. Stakeholder and Problem Analysis.docx 2. Github link: https://github.com/NhlanhlayethuMazibuko/ITC327W-Group-Project.git | Yes | 2026-08-29 | Completed assigned stakeholder and problem-analysis responsibilities and established the project's GitHub repository.
PA Mabusela | 222021446 | Unit 1 / Phase 1 | Activity 1.1 | Current Process & Diagram Specialist | Documented the current accommodation process, identified process participants, prepared the current-process diagram and contributed to defining project scope, constraints and assumptions. | 2026-08-25 | 3 hours | Software Requirement Specification.docx | Yes | 2026-08-29 | Completed assigned current-process and scope responsibilities.
M Mokhele | 221027626 | Unit 1 / Phase 1 | Activity 1.2 | Functional Requirements Writer | Developed the preliminary functional requirements for the student mobile application and management web application based on the stakeholder's identified needs. | 2026-08-27 | 4 hours | FUNCTIONAL REQUIREMENTS.docx | Yes | 2026-08-29 | Completed assigned functional requirements responsibilities.
NP Khotle | 218013010 | Unit 1 / Phase 1 | Activity 1.2 | Non-Functional, System & Integration Requirements Writer | Developed the preliminary non-functional, system and integration requirements and contributed to requirements prioritisation. | 2026-08-27 | 6 hours | Non-Functional, System & Integration Requirements.pdf | Yes | 2026-08-29 | Completed assigned non-functional, system and integration requirements responsibilities.
MN Dlamini | 224093660 | Unit 1 / Phase 1 | Activity 1.3 | SRS Compiler & Editor | Compiled and edited the initial Software Requirements Specification (SRS), combining the group's stakeholder, problem, scope and requirements information. | 2026-08-28 | 15 hours | ITC327W_Work Integrated Learning(2).pdf | Yes | 2026-08-29 | Completed assigned initial SRS compilation and editing responsibilities.
M Lesenyeho | 224081110 | Unit 1 / Phase 1 | Activity 1.3 | Feasibility Analyst – Technical, Operational, Economic, Schedule, Legal & Ethical | Completed the technical, operational, economic, schedule, legal and ethical feasibility analysis for the proposed student accommodation management system. | 2026-08-28 | 12 hours | Feasibility Study.docx | Yes | 2026-08-29 | Completed all assigned feasibility study responsibilities
L Sandi | 223014209 | Unit 1 / Phase 1 | Activity 1.3 | Risk Register Owner | Identified and documented project risks in the Risk Register, including risk categories, likelihood, impact, risk scores, mitigation actions, contingency actions, owners and statuses. | 2026-08-25 | 2 hours | Project Risk Register.xlsx | Yes | 2026-08-25 | Completed the assigned Risk Register responsibilities.
LW Simelane | 224022386 | Unit 1 / Phase 1 | Activity 1.3 | Microsoft Project Scheduler | Created the initial Microsoft Project schedule, including project activities, dates, responsibilities, dependencies and milestones. | 2026-08-27 | 10 hours | WIL Project.mpp | Yes | 2026-08-29 | Completed assigned Microsoft Project scheduling responsibilities.
AL Hadebe | 223000608 | Unit 1 / Phase 1 | Activity 1.3 | Supabase Setup Lead | Created and configured the initial Supabase project and prepared the backend environment for the project. | 2026-08-27 | 2 hours | Supabase link: https://supabase.com/dashboard/project/gtpujwmtglyffnzhbklo | Yes | 2026-08-29 | Completed the assigned Supabase setup responsibilities
JO Molaba | 224067603 | Unit 1 / Phase 1 | Activity 1.3 | Progress Tracker & Coordination Lead | Updated the Project Progress Tracker and coordinated the collection of task progress and evidence from group members. | 2026-08-29 | 8 hours | ITC327W Project Progress Tracker_2026.xlsx | Yes | 2026-08-29 | Responsible for monitoring group progress and coordinating task updates.

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-25 | Unit 1 / Phase 1 | Stakeholder Interview | To understand the current accommodation process, problems, stakeholder needs and required system improvements. | NL Mazibuko, AL Hadebe, MN Dlamini, LW Simelane, NP Khotle, PA Mabusela | Mr Ngubane - Student Accommodation Owner | Accommodation enquiries currently rely on physical viewings, word-of-mouth, WhatsApp groups and taxi association advertising. Bookings and payments are managed manually. Students have difficulty accessing accommodation information remotely, and first-year students may be exposed to accommodation scams. The stakeholder wants students to view availability, apply, book and check status, while management should manage applications, student information, occupancy and accommodation information. | Document the stakeholder needs, define the initial scope and develop preliminary mobile and web requirements. | Stakeholder and Problem Analysis.pdf

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-19 | Unit 1 / Phase 1 | The group experienced difficulty identifying and securing a suitable external stakeholder for the project. | Delayed the start of stakeholder investigation, interview activities and requirements gathering. | Group members contacted potential organisations and followed up until a suitable stakeholder, Big Brother Accommodation, agreed to participate. | NL Mazibuko | 2026-08-21 | Resolved
2026-08-23 | Unit 1 / Phase 1 | The stakeholder took longer than expected to respond to the group's request for information and feedback. | Delayed requirements gathering and slowed progress with documenting the stakeholder's current process and needs. | Followed up with the stakeholder and continued preparing the interview and requirements questions while waiting for responses. | NL Mazibuko | 2026-08-24 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 18 August 2026 – 31 August 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | The group identified Big Brother Accommodation as the external stakeholder, investigated the current accommodation process and problems, conducted a stakeholder interview, gathered stakeholder needs, developed the initial project scope, completed feasibility and risk analysis, and started the SRS, project tracker and project planning activities. | Stakeholder engagement recorded | Yes
What remains incomplete? | Everything is completed for Unit 1/ Phase 1 | Challenges and actions updated | Yes
Why is it incomplete? | Every task is completed | Group reflection completed | Yes
Which contributions were particularly important? | Stakeholder engagement and interview, requirements gathering, feasibility and risk analysis, project planning, SRS preparation and progress tracking were particularly important because they established the project foundation and ensured that the proposed solution was based on the stakeholder's actual needs. | Microsoft Project updated | Yes
Were there participation concerns? | No participation concern recorded at this stage. | GitHub evidence available | Yes
What will the group improve in the next phase? | Improve communication, monitor individual tasks more consistently, finalise requirements earlier, improve Supabase knowledge and manage the project scope to avoid unnecessary features. | Confidential peer check completed | Yes
Main priority for the next phase | Finalise the requirements and system design, confirm the project scope, and prepare for development of the Flutter mobile application, ASP.NET web application and Supabase backend.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Big Brother Student Accommodation Management System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The group learned the importance of understanding the stakeholder's actual problem and current processes before designing a software solution. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The group successfully identified Big Brother Accommodation as the stakeholder, conducted stakeholder engagement, gathered requirements and identified the main challenges with the current manual accommodation process. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Finding a suitable external stakeholder was initially difficult. The stakeholder also took some time to respond to requests, which delayed requirements gathering and stakeholder engagement activities. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided among group members according to assigned responsibilities, including stakeholder engagement, requirements, feasibility and risk analysis, documentation, scheduling, GitHub/Supabase setup and progress tracking.
Did all members contribute fairly? Explain. | Yes. Members contributed fairly by respecting their assigned roles and providing the work and deliverables they were expected to complete.
How did the group handle disagreements or delays? | The group communicated through the WhatsApp group, followed up on outstanding tasks and adjusted responsibilities or timelines where necessary. Stakeholder-response delays were managed by following up and using the information already provided by the stakeholder.
What did the group learn from the stakeholder? | The group learned that the accommodation business currently relies heavily on physical viewing, word-of-mouth and WhatsApp-based advertising, while bookings and payments are largely handled manually. The stakeholder also highlighted the need for easier access to accommodation information, application and booking functionality, better management of student information and improved protection against accommodation scams.
Improvement action 1 for the next phase | Improve task and deadline tracking by ensuring every member records their contribution, evidence and progress regularly.
Improvement action 2 for the next phase | Confirm and review requirements with the stakeholder before moving into design and development to ensure that the proposed system remains aligned with the stakeholder's actual needs.
Priority for the next phase | Finalise the requirements and project planning, then move into system design and development while keeping the agreed scope and stakeholder requirements as the main priority.