## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group N | Completed | 25
Project title | Big Brother Student Accommodation Management System | In Progress | 0
Stakeholder or organisation | Big Brother Student Accommodation | Not Started | 0
Group mentor | N Mabanza, M Mbele, N Grobbelaar | Delayed | 0
Reporting phase | Phase 2 | Blocked | 0
Reporting period | 10 September 2026 - 13 October 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 96.15% | Contribution Summary | Count
Main achievement | The group completed the Phase 2 system design baseline, including the updated SRS, architecture, UML diagrams, ERD, mobile and web interface designs, navigation flows and design alignment checks. | Contribution entries | 20
Main challenge | The main challenge was keeping the architecture, UML, ERD and interface designs consistent as the system design was refined. | Verified entries | 20
Next planned activity | Proceed to development and integration while maintaining alignment with the approved SRS, architecture, database design and interface designs. | Unverified entries | 0
|  | Stakeholder engagements | 2

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | NL Mazibuko | 2026-08-19 | 2026-08-31 | Completed | 100 | Stakeholder and Problem Analysis.docx | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | PA Mabusela | 2026-08-26 | 2026-08-31 | Completed | 100 | Software Requirement Specification.docx | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | MN Dlamini, NP Khotle | 2026-08-24 | 2026-08-31 | Completed | 100 | Non-Functional, System & Integration Requirements.pdf | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | NP Khotle, MN Dlamini | 2026-08-24 | 2026-08-31 | Completed | 100 | Stakeholder and Problem Analysis.docx | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | AL Hadebe, PA Mabusela, NL Mazibuko | 2026-08-25 | 2026-08-31 | Completed | 100 | Stakeholder and Problem Analysis.docx | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | MN Dlamini | 2026-08-25 | 2026-08-31 | Completed | 100 | ITC327W_Work Integrated Learning(1).pdf | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | LW Simelane | 2026-08-19 | 2026-08-31 | Completed | 100 | WIL Project.mpp | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | NL Mazibuko | 2026-08-26 | 2026-08-31 | Completed | 100 | Github link: https://github.com/NhlanhlayethuMazibuko/ITC327W-Group-Project.git | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | AL Hadebe | 2026-08-26 | 2026-08-31 | Completed | 100 | Supabase link: https://supabase.com/dashboard/project/gtpujwmtglyffnzhbklo | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | JO Molaba | 2026-08-24 | 2026-08-31 | Completed | 100 | ITC327W Project Progress Tracker.xlsx | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | JO Molaba, with group input | 2026-08-25 | 2026-08-31 | Completed | 100 | ITC327W Project Progress Tracker.xlsx | Yes |  | Completed
P2-01 | Phase 2 | Activity 3.1 | Review and update the approved SRS for the system design phase | PA Mabusela | 2026-09-10 | 2026-09-13 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-02 | Phase 2 | Activity 3.2 | Develop the System Architecture Diagram and written architecture explanation | M Lesenyelo | 2026-09-11 | 2026-09-18 | Completed | 100 | System Architecture Diagram link: https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&target=blank&highlight=0000ff&edit=_blank&layers=1&nav=1&title=System%20Architecture%20Design%20Diagram.drawio&dark=0#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1-ipbBVGz__jRF2WieEe3WSC3O_ybTdsq%26export%3Ddownload | Yes |  | Completed
P2-03 | Phase 2 | Activity 3.2 | Develop the UML Use Case Diagram with actors and use cases | L Sandi | 2026-09-11 | 2026-09-17 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-04 | Phase 2 | Activity 3.2 | Develop the Flutter mobile Sequence Diagram | NP Khotle | 2026-09-15 | 2026-09-21 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-05 | Phase 2 | Activity 3.2 | Develop the ASP.NET web Sequence Diagram | M Mokhele | 2026-09-15 | 2026-09-21 | Completed | 100 | Web Sequence Diagram link: https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&target=blank&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Sequence%20Diagram(APS.NET).drawio&dark=0#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1pe3ZnGeT62MtFIwFBITfMiQIEaAiwgCh%26export%3Ddownload | Yes |  | Completed
P2-06 | Phase 2 | Activity 3.2 | Develop the Entity Relationship Diagram with entities, attributes, keys and relationships | MN Dlamini | 2026-09-16 | 2026-09-23 | Completed | 100 | ERD link: https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Entity%20Relationship%20Diagram.drawio&dark=0#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1hPSEFW3vkxjzCYKUqcsKeAocBAP2HUcu%26export%3Ddownload | Yes |  | Completed
P2-07 | Phase 2 | Activity 3.3 | Identify required Flutter screens and prepare mobile UI wireframes | L Sandi | 2026-09-18 | 2026-09-27 | Completed | 100 | Flutter UI Wireframes link: Flutter link::::https://www.figma.com/design/wn4Il8WEIqOOEAMzvopEw1/Big-Brother-Student-accommodation-App?node-id=0-1&t=tmuNmyvcqZPeOTw6-1 | Yes |  | Completed
P2-08 | Phase 2 | Activity 3.3 | Identify required ASP.NET pages and prepare web UI wireframes | NL Mazibuko | 2026-09-18 | 2026-09-28 | Completed | 100 | ASP.NET UI Wireframes link: WEB: https://www.figma.com/design/nsfe2RnSzAZCK1aHrkBLQn/Big-Brother-Student-Accom.?node-id=2479-2&t=slbiNpnmbykZmVba-1 | Yes |  | Completed
P2-09 | Phase 2 | Activity 3.3 | Develop mobile and web navigation flows | NL Mazibuko, L Sandi | 2026-09-24 | 2026-10-01 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-10 | Phase 2 | Activity 3.3 | Check alignment between requirements, architecture, use cases, sequences, ERD and interfaces | PA Mabusela, M Lesenyelo, MN Dlamini | 2026-09-29 | 2026-10-05 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-11 | Phase 2 | Activity 3.3 | Obtain and record stakeholder feedback on the system designs | NL Mazibuko | 2026-10-01 | 2026-10-06 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-12 | Phase 2 | Activity 3.3 | Apply agreed design corrections and finalise the system design baseline | L Sandi, JO Molaba, M Lesenyelo, MN Dlamini, NP Khotle, M Mokhele, PA Mabusela, NL Mazibuko, LW Simelane, AL Hadebe | 2026-10-06 | 2026-10-10 | Completed | 100 | Updated Software Requirement Specification.pdf | Yes |  | Completed
P2-13 | Phase 2 | Activity 3.3 | Update Microsoft Project and Gantt Chart, GitHub documentation and project progress records | LW Simelane | 2026-09-10 | 2026-10-13 | Completed | 100 | WIL Project(2).mpp | Yes |  | Completed
P2-14 | Phase 2 | Activity 3.3 | Project Progress Tracker(Tasks and Contributions) | JO Molaba | 2026-09-10 | 2026-10-13 | Completed | 100 | ITC327W Project Progress Tracker.xlsx | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
NL Mazibuko | 222044762 | Unit 1 / Phase 1 | Activity 1.1 and Activity 1.3 | Stakeholder Liaison & Problem Analysis Lead/ Github set up | Identified and confirmed the external stakeholder, documented the stakeholder profile, investigated the current accommodation process, contributed to the problem statement, and created the project GitHub repository. | 2026-08-25 |  | 1. Stakeholder and Problem Analysis.docx 2. Github link: https://github.com/NhlanhlayethuMazibuko/ITC327W-Group-Project.git | Yes | 2026-08-29 | Completed assigned stakeholder and problem-analysis responsibilities and established the project's GitHub repository.
PA Mabusela | 222021446 | Unit 1 / Phase 1 | Activity 1.1 | Current Process & Diagram Specialist | Documented the current accommodation process, identified process participants, prepared the current-process diagram and contributed to defining project scope, constraints and assumptions. | 2026-08-25 |  | Software Requirement Specification.docx | Yes | 2026-08-29 | Completed assigned current-process and scope responsibilities.
M Mokhele | 221027626 | Unit 1 / Phase 1 | Activity 1.2 | Functional Requirements Writer | Developed the preliminary functional requirements for the student mobile application and management web application based on the stakeholder's identified needs. | 2026-08-27 |  | FUNCTIONAL REQUIREMENTS.docx | Yes | 2026-08-29 | Completed assigned functional requirements responsibilities.
NP Khotle | 218013010 | Unit 1 / Phase 1 | Activity 1.2 | Non-Functional, System & Integration Requirements Writer | Developed the preliminary non-functional, system and integration requirements and contributed to requirements prioritisation. | 2026-08-27 | 6 hours | Non-Functional, System & Integration Requirements.pdf | Yes | 2026-08-29 | Completed assigned non-functional, system and integration requirements responsibilities.
MN Dlamini | 224093660 | Unit 1 / Phase 1 | Activity 1.3 | SRS Compiler & Editor | Compiled and edited the initial Software Requirements Specification (SRS), combining the group's stakeholder, problem, scope and requirements information. | 2026-08-28 |  | ITC327W_Work Integrated Learning(2).pdf | Yes | 2026-08-29 | Completed assigned initial SRS compilation and editing responsibilities.
M Lesenyelo | 224081110 | Unit 1 / Phase 1 | Activity 1.3 | Feasibility Analyst – Technical, Operational, Economic, Schedule, Legal & Ethical | Completed the technical, operational, economic, schedule, legal and ethical feasibility analysis for the proposed student accommodation management system. | 2026-08-28 | 12 hours | Feasibility Study.docx | Yes | 2026-08-29 | Completed all assigned feasibility study responsibilities
L Sandi | 223014209 | Unit 1 / Phase 1 | Activity 1.3 | Risk Register Owner | Identified and documented project risks in the Risk Register, including risk categories, likelihood, impact, risk scores, mitigation actions, contingency actions, owners and statuses. | 2026-08-25 | 2 hours | Project Risk Register.xlsx | Yes | 2026-08-25 | Completed the assigned Risk Register responsibilities.
LW Simelane | 224022386 | Unit 1 / Phase 1 | Activity 1.3 | Microsoft Project Scheduler | Created the initial Microsoft Project schedule, including project activities, dates, responsibilities, dependencies and milestones. | 2026-08-27 |  | WIL Project.mpp | Yes | 2026-08-29 | Completed assigned Microsoft Project scheduling responsibilities.
AL Hadebe | 223000608 | Unit 1 / Phase 1 | Activity 1.3 | Supabase Setup Lead | Created and configured the initial Supabase project and prepared the backend environment for the project. | 2026-08-27 | 2 hours | Supabase link: https://supabase.com/dashboard/project/gtpujwmtglyffnzhbklo | Yes | 2026-08-29 | Completed the assigned Supabase setup responsibilities
Molaba JO | 224067603 | Unit 1 / Phase 1 | Activity 1.3 | Progress Tracker & Coordination Lead | Updated the Project Progress Tracker and coordinated the collection of task progress and evidence from group members. | 2026-08-29 | 8 hours | ITC327W Project Progress Tracker_2026.xlsx | Yes | 2026-08-29 | Responsible for monitoring group progress and coordinating task updates.
L Sandi, AL Hadebe, PA Mabusela | 223014209, 223000608, 222021446 | Phase 2 | Activity 3.2 and 3.3 | Lead Mobile UI Designer & Use Case Analyst | Completed the use case analysis and mobile interface design, including Flutter screen planning and mobile wireframes. | 2026-09-14 | 9 hours | Flutter link::::https://www.figma.com/design/wn4Il8WEIqOOEAMzvopEw1/Big-Brother-Student-accommodation-App?node-id=0-1&t=tmuNmyvcqZPeOTw6-1 | Yes | 2026-10-10 | Completed assigned Phase 2 mobile UI and use case responsibilities.
NL Mazibuko | 222044762 | Phase 2 | Activity 3.3 | Lead Web UI Designer | Completed the ASP.NET page list, web navigation flow and management-side web UI wireframes, aligned with the approved requirements and database fields. | 2026-09-18 | 8 hours | WEB: https://www.figma.com/design/nsfe2RnSzAZCK1aHrkBLQn/Big-Brother-Student-Accom.?node-id=2479-2&t=slbiNpnmbykZmVba-1 | Yes | 2026-10-10 | Completed assigned Phase 2 web interface design responsibilities.
M Lesenyelo | 224081110 | Phase 2 | Activity 3.2 and 3.3 | System Architect | Completed the system architecture design and helped align the architecture with the SRS, UML, ERD and interface designs. | 2026-09-15 | 19 hours | System Architecture Diagram link: https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&target=blank&highlight=0000ff&edit=_blank&layers=1&nav=1&title=System%20Architecture%20Design%20Diagram.drawio&dark=0#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1-ipbBVGz__jRF2WieEe3WSC3O_ybTdsq%26export%3Ddownload | Yes | 2026-10-10 | Completed assigned architecture and alignment responsibilities.
MN Dlamini | 224093660 | Phase 2 | Activity 3.2 and 3.3 | Database Architect & ERD Lead | Completed the ERD and checked that interface data and system requirements were supported by the database design. | 2026-09-17 | 11 hours | ERD link: https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Entity%20Relationship%20Diagram.drawio&dark=0#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1hPSEFW3vkxjzCYKUqcsKeAocBAP2HUcu%26export%3Ddownload | Yes | 2026-10-10 | Completed assigned database design responsibilities.
NP Khotle | 218013010 | Phase 2 | Activity 3.2 | Mobile Sequence Lead | Completed the Flutter mobile sequence diagram showing the required user, application and Supabase interactions. | 2026-09-25 | 6 hours | Updated Software Requirement Specification.pdf | Yes | 2026-10-10 | Completed assigned mobile sequence design responsibilities.
M Mokhele | 221027626 | Phase 2 | Activity 3.2 | Web Sequence Lead | Completed the ASP.NET web sequence diagram showing management interactions with the web application and Supabase. | 2026-09-27 | 6 hours | Web Sequence Diagram link: https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&target=blank&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Sequence%20Diagram(APS.NET).drawio&dark=0#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1pe3ZnGeT62MtFIwFBITfMiQIEaAiwgCh%26export%3Ddownload | Yes | 2026-10-10 | Completed assigned web sequence design responsibilities.
PA Mabusela, AL Hadebe | 222021446, 223000608 | Phase 2 | Activity 3.1 and 3.3 | Design Alignment & SRS Coordinator | Updated the SRS for the design phase and coordinated the alignment review across requirements, architecture, UML, ERD and interfaces. | 2026-09-30 | 18 hours | Updated Software Requirement Specification.pdf | Yes | 2026-10-10 | Completed assigned SRS and design-alignment responsibilities.
NL Mazibuko | 222044762 | Phase 2 | Activity 3.3 | Stakeholder Manager | Coordinated the design feedback process, recorded stakeholder feedback and communicated required design adjustments to the group. | 2026-10-02 | 10 hours | Updated Software Requirement Specification.pdf | Yes | 2026-10-10 | Completed assigned stakeholder feedback responsibilities.
LW Simelane, JO Molaba | 224022386, 224067603 | Phase 2 | Activity 3.3 | Project Manager | Monitored Phase 2 completion, coordinated design milestones and ensured the project schedule and progress records were updated. | 2026-10-06 | 8 hours | Updated MS Project.mpp, ITC327W Project Progress Tracker_2026.xlsx | Yes | 2026-10-10 | Completed assigned Phase 2 project scheduling and coordination responsibilities.
NL Mazibuko | 222044762 | Phase 2 | Activity 3.3 | Documentation & GitHub Repository Manager | Organised Phase 2 design evidence, updated GitHub documentation and prepared the final Phase 2 evidence package. | 2026-10-08 | 6 hours | GitHub Phase 2 documentation; Phase 2 Evidence Package | Yes | 2026-10-10 | Completed assigned documentation and repository responsibilities.

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-25 | Unit 1 / Phase 1 | Stakeholder Interview | To understand the current accommodation process, problems, stakeholder needs and required system improvements. | NL Mazibuko, AL Hadebe, MN Dlamini, LW Simelane, NP Khotle, PA Mabusela | Mr Ngubane - Student Accommodation Owner | Accommodation enquiries currently rely on physical viewings, word-of-mouth, WhatsApp groups and taxi association advertising. Bookings and payments are managed manually. Students have difficulty accessing accommodation information remotely, and first-year students may be exposed to accommodation scams. The stakeholder wants students to view availability, apply, book and check status, while management should manage applications, student information, occupancy and accommodation information. | Document the stakeholder needs, define the initial scope and develop preliminary mobile and web requirements. | Stakeholder and Problem Analysis.pdf
2026-10-01 | Phase 2 | Online Meeting | Review the proposed system architecture, UML, ERD and mobile/web interface designs with the stakeholder and confirm that the design remains aligned with the accommodation business needs. | NL Mazibuko | Mr Ngubane - Student Accommodation Owner | The proposed design was reviewed against the stakeholder requirements, with attention to accommodation information, applications, bookings, student information, availability, payment-status information, maintenance/breakages and feedback. | Apply agreed design adjustments and retain the feedback record as evidence for the final design baseline. | WhatsApp Feedback Screenshot.pdf

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-19 | Unit 1 / Phase 1 | The group experienced difficulty identifying and securing a suitable external stakeholder for the project. | Delayed the start of stakeholder investigation, interview activities and requirements gathering. | Group members contacted potential organisations and followed up until a suitable stakeholder, Big Brother Accommodation, agreed to participate. | NL Mazibuko | 2026-08-21 | Resolved
2026-08-23 | Unit 1 / Phase 1 | The stakeholder took longer than expected to respond to the group's request for information and feedback. | Delayed requirements gathering and slowed progress with documenting the stakeholder's current process and needs. | Followed up with the stakeholder and continued preparing the interview and requirements questions while waiting for responses. | NL Mazibuko | 2026-08-24 | Resolved
2026-09-17 | Phase 2 | Keeping the architecture, UML diagrams, ERD, SRS and mobile/web interfaces consistent while different members developed the design artefacts in parallel. | Changes to requirements or one design artefact could create inconsistencies elsewhere, increasing review time and risking conflicting documentation. | Used a cross-design alignment review to compare the SRS, architecture, use cases, sequence diagrams, ERD and interfaces; corrected identified mismatches before confirming the design baseline. | NL Mazibuko, M Lesenyelo, MN Dlamini, NP Khotle, L Sandi, AL Hadebe, M Mokhele | 2026-09-30 | Resolved
2026-10-20 | Phase 2 | Keeping the interface designs within the approved scope, particularly where requested features needed to be represented as prototype-level functionality. | Adding unsupported functions could increase development effort and contradict the SRS, especially for payment handling and reporting. | Checked proposed screens and functions against the SRS. Kept payment handling to EFT payments rather than a live payment gateway, and limited reports to basic summaries. | L Sandi | 2026-10-03 | Resolved
2026-10-01 | Phase 2 | Incorporating stakeholder feedback without introducing functionality outside the approved scope. | Late design changes could affect completed interfaces and alignment work. | Recorded stakeholder feedback, checked requested changes against the SRS and applied only agreed in-scope corrections. | NL Mazibuko | 2026-10-06 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 2 | Initial or updated SRS completed | Yes
Reporting period | 2026-09-10 – 2026-10-13 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | The group completed the Phase 2 system design work. This included reviewing and updating the SRS, developing the system architecture, UML use case and sequence diagrams, ERD, Flutter mobile interfaces, ASP.NET web interfaces, navigation flows and cross-design alignment checks. Stakeholder design feedback was recorded and the agreed design baseline was finalised. | Stakeholder engagement recorded | Yes
What remains incomplete? | No major Phase 2 deliverable remains incomplete. The project is ready to move from design into development and integration. | Challenges and actions updated | Yes
Why is it incomplete? | Not applicable because the planned Phase 2 design deliverables were completed. Any minor corrections were handled during the alignment and review activities. | Group reflection completed | Yes
Which contributions were particularly important? | Architecture, UML, ERD, interface design, stakeholder review, design alignment and progress/documentation updates were particularly important because they established a consistent baseline for development. | Microsoft Project updated | Yes
Were there participation concerns? | No participation concern recorded. All ten members completed assigned Phase 2 responsibilities. | GitHub evidence available | Yes
What will the group improve in the next phase? | Maintain tighter alignment between development tasks and the approved design, continue updating the tracker regularly, and record evidence as each development and integration task is completed. | Confidential peer check completed | Yes
Main priority for the next phase | Begin development and integration of the Flutter mobile application, ASP.NET web application and Supabase backend using the approved Phase 2 design baseline.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 2 | Length | Approximately 300–400 words in total.
Project title | Big Brother Student Accommodation Management System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The group learned that system design requires continuous alignment between requirements, architecture, UML diagrams, database design and user interfaces. A change in one artefact can affect other parts of the system, so reviewing the designs together was important before development. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The group successfully produced the main Phase 2 design artefacts, including the architecture, use case diagram, sequence diagrams, ERD and mobile/web interfaces. The team also reviewed the designs against the approved requirements and prepared the project for development. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The main difficulty was keeping the different design artefacts consistent while several members were working on them at the same time. It was also necessary to control the scope so that interface designs did not introduce functions that were not supported by the approved requirements. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to the Phase 2 responsibilities, with members covering mobile UI and use cases, web UI, architecture, database/ERD, mobile and web sequences, SRS/design alignment, stakeholder feedback, project management and documentation/GitHub.
Did all members contribute fairly? Explain. | Yes. For the purposes of this Phase 2 record, all ten members completed the responsibilities assigned to them and contributed to the required design deliverables.
How did the group handle disagreements or delays? | The group handled design differences by reviewing the relevant requirements and checking the affected artefacts together. Alignment reviews were used to identify and resolve inconsistencies before the design baseline was finalised.
What did the group learn from the stakeholder? | The stakeholder requirements continued to guide the design, particularly the need for easier access to accommodation information, student applications and bookings, management control of student information, accommodation management, simulated payment-status information and improved protection of student information.
Improvement action 1 for the next phase | Keep the development work aligned with the approved design and update the progress tracker and evidence records regularly.
Improvement action 2 for the next phase | Use the approved SRS and design baseline as the reference point for development, integration and testing, and avoid adding features that are outside the agreed scope.
Priority for the next phase | Start development and integration while continuing to monitor progress, record evidence and validate the implementation against the approved system design.